## TOBS Cover page
The Online Book Store Application
Cover Page
| Prepared By | Reviewed By | Apporved By
Name | Ngan Do
Role | Test Engnieer
Date | 07/10/20201
Signature | Ngan Do

## TOBS Test Scenario
TOBS Application
Module | Scenario_id | Scenario_Name | Scenario_Description | Reference_Document | Requirement
Delete topic | TS_TOBS_001 | Validate the Remove button | To check Remove button active | SRS01 | RO7
Edit topic | TS_TOBS_002 | Validate the Valid information | To check wheather the user enter Valid detail can able to edit | SRS02 | RO7
Edit topic | TS_TOBS_003 | Validate the Invalid information | To check wheather the user enter Invalid detail can able to edit or not | SRS02 | RO7

## TOBS Test Cases
TOBS Application
Test Scenario_id | Test Case_id | Test Case_Description | Pre-Requisite | Test Data Parameters | Steps to Execute | Test Data | Expected Result | Actual Result | Test Result | Defect_id | Remarks | Priority | Tech Used
TS_TOBS_001 | TC_TOBS_01 | To check Remove button is active or not | Admin loged into the system | <Remove - Button> | 5) Click on Remove button |  | It should redirect to Topic page without this topic | It should redirect to Topic page without this topic | Passed |  |  | High
TS_TOBS_002 | TC_TOBS_02 | To check the user can able to edit topic with valid details. | Admin loged into the system |  | 1) Click Add Catalog button in Topic page | edit topic page | The edit topic page should open. | The edit topic page open. | Passed |  |  | High
|  |  |  | <ID - Text Box> | 2) Enter the ID | 4 | The ID should be displayed in the textbox | The ID displayed in the textbox
|  |  |  | <Name - Text Box> | 3) Enter the name | Love | The name should be displayed in the textbox | The name displayed in the textbox
|  |  |  | <Parent of topic - Drop down box> | 4) Choose parent of topic in dbs | New product | The parent of topic should be displayed in this field | The parent of topic displayed in this field
|  |  |  | <Add - Button> | 5) Click on Add button |  | It should redirect to Topic page with new topic | It redirects to Topic page with new topic
TS_TOBS_002 | TC_TOBS_03 | To check all fields are mandatory | Admin loged into the system |  | 1) Click Add Catalog button in Topic page | edit topic page | The edit topic page should open. | The edit topic page open. | Passed |  |  | High
|  |  |  | <ID - Text Box> | 2) Enter the ID = empty
|  |  |  | <Name - Text Box> | 3) Enter the name = empty
|  |  |  | <Parent of topic - Drop down box> | 4) Choose parent of topic in dbs | New product | The parent of topic should be displayed in this field | The parent of topic displayed in this field
|  |  |  | <Add - Button> | 5) Click on Add button |  | It should redirect to Error page | It redirects to Error page
| TC_TOBS_04 | To check the user enter valid details with prefix or sufix space(s) | Admin loged into the system |  | 1) Click Add Catalog button in Topic page | edit topic page | The edit topic page should open. | The edit topic page open. | Passed |  |  | High
|  |  |  | <ID - Text Box> | 2) Enter the ID | 1 | The ID should be displayed in the textbox | The ID displayed in the textbox
|  |  |  | <Name - Text Box> | 3) Enter the name | Love | The name should be displayed in the textbox | The name displayed in the textbox
|  |  |  | <Parent of topic - Drop down box> | 4) Choose parent of topic in dbs | New product | The parent of topic should be displayed in this field | The parent of topic displayed in this field
|  |  |  | <Add - Button> | 5) Click on Add button |  | It should redirect to Error page | It redirects to Error page
| TC_TOBS_05 | To check the user can able to edit ID is not digit | Admin loged into the system |  | 1) Click Add Catalog button in Topic page | edit topic page | The edit topic page should open. | The edit topic page open. | Passed |  |  | High
|  |  |  | <ID - Text Box> | 2) Enter the ID | ngan | The ID should be displayed in the textbox | The ID displayed in the textbox
|  |  |  | <Name - Text Box> | 3) Enter the name | Romance | The name should be displayed in the textbox | The name displayed in the textbox
|  |  |  | <Parent of topic - Drop down box> | 4) Choose parent of topic in dbs | New product | The parent of topic should be displayed in this field | The parent of topic displayed in this field
|  |  |  | <Add - Button> | 5) Click on Add button |  | It should redirect to Error page | It redirects to Error page
| TC_TOBS_06 | To check the user can able to edit name is not characters | Admin loged into the system |  | 1) Click Add Catalog button in Topic page | edit topic page | The edit topic page should open. | The edit topic page open. | Passed |  |  | High
|  |  |  | <ID - Text Box> | 2) Enter the ID | 1 | The ID should be displayed in the textbox | The ID displayed in the textbox
|  |  |  | <Name - Text Box> | 3) Enter the name | 1234 | The name should be displayed in the textbox | The name displayed in the textbox
|  |  |  | <Parent of topic - Drop down box> | 4) Choose parent of topic in dbs | New product | The parent of topic should be displayed in this field | The parent of topic displayed in this field
|  |  |  | <Add - Button> | 5) Click on Add button |  | It should redirect to Error page | It redirects to Error page

## TOBS Defect Log
IDBI Bank Application
Test Case_id(Failed) | Defect_id | Reproducability | Defect Description | Defect in cycle | Defect in Version | Severity | Priority | Steps to reproduce | TestData | Defect Status | Reported By | Reported Date | Phase of Origin | Defect type | Cause of Defect | Resolution | Resolved By | Resolved Date | Remarks | Closed By | Closed Date

## TOBS RTM
TOBS Application
Requirement_id | Test Scenerio_id | Test Case_id | Test Result | Defect_id
RO3 | IDBI Valid APP_001 | TC_TOBS_01 | Passed
| IDBI InValid APP_002 | TC_TOBS_02 | Passed
|  | TC_TOBS_03 | Passed
|  | TC_TOBS_04 | Passed
|  | TC_TOBS_05 | Passed